## Cover Page
2020 Goals & Objectives
March 11, 2020
ETC Cooperative

## Organizational Goals
#REF!
ETC Coop 2020 Organizational Goals
|  | Timeline | Responsibility | Quarterly Progress Updates | Comments
Protocol Stewardship
1 | Protect the protocol by avoiding the introduction of changes to the ETC protocol which are counter to ETC philosophy and avoid governance capture. | Ongoing | Bob and Yaz
2 | Protect the mainnet by avoiding any major denial-of-service or other security incidents during 2020. | Ongoing | Bob and Yaz
3 | Successful upgrade of the ETC network to the "Phoenix" hard-fork in June 2020, adding "Instanbul support" without a chain-split. | Q2 | Bob and Yaz
4 | Successful upgrade of the ETC network to a further hardfork in Q4 2020 (unless delayed) which will address the remaining blockers to ETC being considered "feature complete". | Q4 | Bob and Yaz
Grassroots Communication & Marketing
5 | Attend major Ethereum community conferences and hackathons and document connections made there. Attract 5 prestige "anchor tenant" projects from the Ethereum ecosystem (note that attendence at conferences will level off after Q1 due to Coronavirus). | Q4 | Bob and Yaz
6 | Deliver ETC website in at least English, German, Russian, and Mandarin. | Q4 | Bob
7 | Attract additional funding for ETC Cooperative before the end of the 2020 fiscal year. | Q4 | Bob
Partnerships & Outreach
8 | Establish a Specifications Ring within Ethereum Magicians and to gather stakeholders from ETH, ETC and EEA there. | Q2 | Bob
9 | Deliver a modular specification for Ethereum by the end of 2020 (probably via the EEA with input from Ethereum Magicians group) which spans ETH, ETC and EEA requirements. This will pivot thinking about “Ethereum”. | Q4 | Bob
10 | Give presentations to Hyperledger meetup attendees on Ethereum Stack and ETC (if meetups are occurring). | Ongoing | Yaz
Development
11 | Continue to support Hyperledger Besu through pending 2020 hardforks through grants. The goal is to attain 10% “market share” for Hyperledger Besu on ETC mainnet by end of 2020. | Q4 | Bob
12 | Attract further users for EtherCluster (now part of Hyperledger Labs). Set of a target of attracting an additional non-ETC Cooperative maintainer by end of 2020. | Q4 | Yaz
13 | Migrate BlockScout instances for ETC to use Hyperledger Besu rather than Parity-Ethereum. Address shortfalls as required ourselves or with ETC bounties. | Q2 | Yaz
14 | Support Keccak256 POW change proposal by adding support to Hyperledger Besu and establishing a high quality testnet with Whiteblock Genesis. Work with miners to build consensus and get support into mining software. | Q1/Q2 | Bob
15 | Foster Ethereum LLVM community by setting up a Telegram channel and gather interested parties there. Speak to Hyperledger TSC and push for contribution of SOLL to Hyperledger Labs. | Q1/Q2 | Bob
16 | Add Connext state channels support. The goal is to have Connext ETC channels live in March 2020. | Q1 | Bob
17 | Add fork monitor and ethstats dashboards | Q2 | Yaz
18 | Work on 1-2 major technical projects that use ETC as a part of developer marketing. | Q4 | Yaz
19 | Run EEA Testnet and participate in Testnet Working Group for EEA. | Ongoing | Yaz
Governance
20 | Prepare Board of Directors monthly update reports from Q1 on, within 30 days of the end of the month. | Ongoing | Bob and Alison
21 | Prepare a quarterly ETC Coop transparency report with financial information, within 6 weeks of the end of the quarter. | Ongoing | Bob and Alison
22 | Adhere to processes and policies set out in the Governance manual and executed policies. | Ongoing | Bob, Yaz and Alison
23 | Comply with all Form 990 compliance requirements for 501(c)(3) reporters. | Ongoing | Bob and Alison
24 | Implement a grant program with documentation, standards, and reporting requirements. | Ongoing | Bob and Alison