## Cover Page
2020 Goals & Objectives
Updated for Q1 2020
ETC Cooperative

## Organizational Goals
#REF!
ETC Coop 2020 Organizational Goals
|  | Timeline | Responsibility | Notes on means of assessment | Quarterly Progress Updates | Progress Tracker
Protocol Stewardship
1 | Protect the protocol by avoiding the introduction of changes to the ETC protocol which are counter to ETC philosophy and avoid governance capture. | Ongoing | Bob and Yaz | Subjective self-assessment by Bob, but will be obvious from "noise" around contentious changes. | Success in Q1 | On track to meet goals/objective
2 | Protect the mainnet by avoiding any major denial-of-service or other security incidents during 2020. | Ongoing | Bob and Yaz | Self-assessment by Bob, but fairly objective. | Success in Q1 | On track to meet goals/objective
3 | Successful upgrade of the ETC network to the "Phoenix" hard-fork in June 2020, adding "Instanbul support" without a chain-split. | Q2 | Bob and Yaz |  | Lots of discussion on ETC Discord. Outreach to node operators imminent. Appears to be on track. | On track to meet goals/objective
4 | Successful upgrade of the ETC network to a further hardfork in Q4 2020 (unless delayed) which will address the remaining blockers to ETC being considered "feature complete". | Q4 | Bob and Yaz |  | To early to determine progress | To early to determine
Grassroots Communication & Marketing
5 | Attend major Ethereum community conferences and hackathons (ETHDenver, ETHCC, Consensus, DEVCON) and document connections made there. Attract 5 prestige "anchor tenant" projects from the Ethereum ecosystem (note that attendence at conferences will level off after Q1 due to Coronavirus). EDCON was cancelled already and Consensus looks likely to be cancelled too. | Q4 | Bob and Yaz | "Prestige" is a little hard to gauge, but the goal is to attract projects which have name recognition - ie. Maker, Compound, Uniswap, Synthetix, Gnosis, Aragon, Status | We attended FOSDEM, ETHDenver, ETHLondon, ETHCC and EEA meetings in Q1 before the lockdowns began. There will be an ETC "Foundations" virtual conference during Consensus 2020. Outreach will continue online. In current world financial situation, it will be hard to get new projects going and may have to reassess this goal in Q2. | May or may not be on track to meet goals/objective
6 | Deliver ETC website in at least English, German, Russian, and Mandarin. | Q4 | Bob |  | The website content refresh is almost complete (volunteer-driven). Translations still on track for Q4. | On track to meet goals/objective
7 | Attract additional funding for ETC Cooperative before the end of the 2020 fiscal year by establishing a membership scheme (individual and corporate) along the lines of those operated by the Linux Foundation, the OSI, the EFF, etc. | Q4 | Bob | Goal is to raise an additional $50K USD outside of Grayscale | No significant outreach or plan has begun yet. We will continue to brainstorm ideas/solutions in Q2 and will update then, if any progress has been made. | May or may not be on track to meet goals/objective
Partnerships & Outreach
8 | Establish a Specifications Ring within Ethereum Magicians and to gather stakeholders from ETH, ETC and EEA there. | Q2 | Bob | Active rings can be seen at https://ethereum-magicians.org/ | A Ring has not launched yet (ETHCC was original plan). With regular conferences not taking place, this may have to be postponed until next year. | May or may not be on track to meet goals/objective
9 | Deliver a modular specification for Ethereum by the end of 2020 (probably via the EEA with input from Ethereum Magicians group) which spans ETH, ETC and EEA requirements. This will pivot thinking about “Ethereum”. | Q4 | Bob | EEA Client Spec v5 is due for release Q2 and v6 in Q4. See https://entethalliance.github.io/client-spec/spec.html. By Q4 the specification should be sufficiently modular to cover ETC clients. | Just starting to engage with Technical Spec WG, further work to be done throughout the year. | To early to determine
10 | Give 4 presentations to Hyperledger meetup attendees on Ethereum Stack and ETC (if meetups are occuring). | Ongoing | Yaz |  | One talk delivered so far, with other talks planned. On track to meet goals. | On track to meet goals/objective
Development
11 | Continue to support Hyperledger Besu through pending 2020 hardforks through grants. The goal is to attain 10% “market share” for Hyerledger Besu on ETC mainnet by end of 2020. | Q4 | Bob | Measure with https://etcnodes.org | Besu has been updated for Atzlan and then for Phoenix. "Market share" still very low. | May or may not be on track to meet goals/objective
12 | Attract further users for EtherCluster (now part of Hyperledger Labs). Set of a target of attracting an additional non-ETC Cooperative maintainer by end of 2020. | Q4 | Yaz |  | Will assess in Q2 | To early to determine
13 | Migrate BlockScout instances for ETC to use Hyperledger Besu rather than Parity-Ethereum. Address shortfalls as required ourselves or with ETC bounties. | Q2 | Yaz | Shortfalls here being features which are commonly used in other block explorers and which will need to be added to BlockScout. We will build an explicit list of these to be tracked over the year. | Waiting on POA for a SOW and determine a plan of action | To early to determine
14 | Support Keccak256 POW change proposal by adding support to Hyperledger Besu and establishing a high quality testnet with Whiteblock Genesis. Work with miners to build consensus and get support into mining software. | Q1/Q2 | Bob |  | Initial POC and testnet delivered by Whiteblock | On track to meet goals/objective
15 | Foster Ethereum LLVM community by setting up a Telegram channel and gather interested parties there. Speak to Hyperledger TSC and push for contribution of SOLL to Hyperledger Labs. | Q1/Q2 | Bob | This is pretty subjective but a healthy ecosystem is self-evident. One specific and measurable goal would be for SOLL to be production ready by the end of 2020. | Work ongoing and on track to meet goals | On track to meet goals/objective
16 | Add Connext state channels support. The goal is to have Connext ETC channels live in March 2020. | Q1 | Bob |  | Work has commenced with Connext and on track for Q2 deliverables | On track to meet goals/objective
17 | Add fork monitor and ethstats dashboards | Q2 | Yaz |  | To be started in Q2 | To early to determine
18 | Work on 1-2 major technical projects that use ETC as a part of developer marketing. | Q4 | Yaz |  | Currently working on Connext and EEA testnet. On track to meet deliverables | On track to meet goals/objective
19 | Run EEA Testnet and participate in Testnet Working Group for EEA. | Ongoing | Yaz |  | Success in Q1 and ongoing | On track to meet goals/objective
Governance/Finance
20 | Prepare Board of Directors monthly update reports from Q1 on, within 30 days of the end of the month. | Ongoing | Bob and Alison | Based on meeting targets for submission | Q1 report being prepared with monthly reports to commence in April | On track to meet goals/objective
21 | Prepare a quarterly ETC Coop transparency report with financial information, within 6 weeks of the end of the quarter. | Ongoing | Bob and Alison | Based on meeting targets for submission | Q1 report being prepared and will be published before Mid-May | On track to meet goals/objective
22 | Adhere to processes and policies set out in the Governance manual and executed policies. | Ongoing | Bob, Yaz and Alison |  | Success in Q1 | On track to meet goals/objective
23 | Comply with all Form 990 compliance requirements for 501(c)(3) reporters, as per the compliance worksheet (100% compliance expected) | Ongoing | Bob and Alison | Form 990 compliance checklist | Success in Q1 | On track to meet goals/objective
24 | Implement a grant program with documentation, standards, and reporting requirements in Q2 or Q3 2020 | Ongoing | Bob and Alison | Grant program documentation completed during timeframe specified | Not started. Due Q2 or Q3 | To early to determine

## Sheet1 (hidden)
To early to determine
On track to meet goals/objective
May or may not be on track to meet goals/objective
Not on track to meet goals/objective